## Timeline
FlowBooks Invoice Upload System — Implementation Timeline and Milestones
Scope: FIRS/NRS e-Invoicing invoice upload API (create / status / payment notify). Updated July 2026.
ID | Phase | Milestone | Target | Status | Description
M1.1 | 1 — Foundation | NRS/FIRS payload alignment | Nov 2025 | ✅ Complete | Align create/status/notify with FIRS/NRS e-invoicing schema (IRN, parties, lines, tax, totals).
M1.2 | 1 — Foundation | Invoice upload API live | Dec 2025 | ✅ Complete | POST /api/v1/invoice/create, /status, /payment/notify implemented.
M2.1 | 2 — Auth & Platform | OAuth 2.0 + JWT | Feb 2026 | ✅ Complete | Client Credentials token endpoint; Bearer JWT on invoice routes.
M2.2 | 2 — Auth & Platform | Business-scoped access | Mar 2026 | ✅ Complete | OAuth client bound to NRS business_id; mismatch returns 403.
M2.3 | 2 — Auth & Platform | KYC Connect credentials | Mar 2026 | ✅ Complete | Sandbox (fbk_test_) / production (fbk_live_) credential issuance after KYC.
M3.1 | 3 — Docs & UX | Public API documentation | Apr 2026 | ✅ Complete | /e-invoicing-api-docs, OpenAPI JSON, Postman collection.
M3.2 | 3 — Docs & UX | Developer tools UI | May 2026 | ✅ Complete | NRS Business/Service ID save; generate/view OAuth credentials.
M4.1 | 4 — Security | App hardening | Jun 2026 | ✅ Complete | Helmet/HSTS/CSP, secret hygiene, production logging controls.
M4.2 | 4 — Security | Request validation (Joi) | Jul 2026 | ✅ Complete | Joi for create/status/notify. payment_status: PENDING, PAID, REJECTED, PARTIAL.
M4.3 | 4 — Security | OAuth rate limiting | Jul 2026 | ✅ Complete | ~20 failed token requests / 15 min / IP on /oauth/token.
M4.4 | 4 — Security | Formal VAPT | Jul–Aug 2026 | 🔄 In progress | Third-party VAPT scoped to e-invoicing API only.
M5.1 | 5 — Launch | UAT / pilot | Jul–Sep 2026 | 🔲 Planned | Pilot merchants with sandbox upload; validate IRN, status, PARTIAL notify.
M5.2 | 5 — Launch | Production rollout | Aug–Oct 2026 | 🔲 Planned | Live credentials, monitoring, optional NRS upstream transmission.
M5.3 | 5 — Compliance | SI/APP approval | Sep–Dec 2026 | 🔲 Planned | Complete FIRS SI / Access Point Provider approval package.

## Phases
Phase Summary
Phase | Period | Focus
Phase 1 — Foundation | Sep–Dec 2025 | Invoice upload contract; local SI sandbox store; optional NRS upstream proxy.
Phase 2 — Auth & Platform | Dec 2025 – Mar 2026 | OAuth Client Credentials → JWT; KYC Connect credentials; business_id binding.
Phase 3 — Docs & UX | Feb–May 2026 | Public docs, Postman, Developer tools for NRS IDs and keys.
Phase 4 — Security | May–Aug 2026 | Hardening, Joi validation, token rate limit, formal VAPT.
Phase 5 — Launch & Compliance | Jul–Dec 2026 | UAT/pilot, production rollout, SI/APP approval.

## Upload APIs
In-Scope Invoice Upload APIs
Method | Endpoint | Purpose
POST | /api/v1/invoice/oauth/token | Obtain access token (OAuth 2.0 Client Credentials)
POST | /api/v1/invoice/create | Upload / create invoice
POST | /api/v1/invoice/status | Lookup invoice / clearance status
POST | /api/v1/invoice/payment/notify | Notify payment status: PENDING ¦ PAID ¦ REJECTED ¦ PARTIAL
Payment status values for /payment/notify:
PENDING, PAID, REJECTED, PARTIAL (amount required when PARTIAL)